## Project wise Time Impact
Which projects are over or under budgeted hours?
Row Labels | Time Impact
Project E | 366
Project D | 144
Project B | -108
Project A | -204
Project C | -318
Grand Total | -120
Project E & D is completeing under time but Project A,B, C is Taking long time

## Project wise cost Impact
Which projects are over or under budgeted costs?
Row Labels | Cost Impact
Project C | -27300
Project A | -14550
Project B | -4500
Project D | 19500
Project E | 36240
Grand Total | 9390
Project C, A,B is taking much amount then actual but project D& E is saving much amount

## Employee wise Time Impact
Which personnel are over or under budgeted hours?
Row Labels | Time Impact | Time Impact
Larry | 480 | under budgeted hours
Inigo | 300 | under budgeted hours
Erica | 60 | Over budgeted hours
Crystal | 0 | Over budgeted hours
Sondra | 0 | under budgeted hours
Tom | -30 | Over budgeted hours
Sarah | -60 | Over budgeted hours
Jenny | -60 | under budgeted hours
Jim | -90 | Over budgeted hours
Gail | -96 | Over budgeted hours
Stanley | -144 | under budgeted hours
Monique | -240 | Over budgeted hours
George | -240 | Over budgeted hours
Grand Total | -120 | OVER HOURS
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Employee wise Cost Impact
Which personnel cost the most? The least?
Emp Personal | Cost Impact
Monique | -25200
George | -14400
Jim | -8100
Stanley | -7200
Gail | -4800
Jenny | -4500
Sarah | -4500
Tom | -1050
Crystal | 0
Sondra | 0
Erica | 8400
Inigo | 28500
Larry | 42240
Grand Total | 9390
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project vs time vs cost
Row Labels | Time Impact | Cost Impact
Project A | -204 | -14550
Project B | -108 | -4500
Project C | -318 | -27300
Project D | 144 | 19500
Project E | 366 | 36240
Grand Total | -120 | 9390

## Task, Duration vs resource
TASK | Resource count | Time Impact
AT1 | 5 | -192
AT2 | 2 | 0
AT3 | 2 | -12
BT1 | 3 | -96
BT2 | 3 | 15
BT3 | 3 | -27
CT1 | 4 | 0
CT2 | 3 | -282
CT3 | 3 | 3
CT4 | 2 | -42
CT5 | 2 | 3
DT1 | 4 | 300
DT2 | 4 | -42
DT3 | 3 | -72
DT4 | 3 | -42
ET1 | 3 | -72
ET2 | 4 | 438
Grand Total | 53 | -120

## Task Employee Vs Cost
Sum of Cost of Project | Employees
Task | Crystal | Erica | Gail | George | Inigo | Jenny | Jim | Larry | Monique | Sarah | Sondra | Stanley | Tom | Grand Total
AT1 |  |  | -2100 |  |  | 0 | -10800 |  | 0 |  |  |  | -1050 | -13950
AT2 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
AT3 |  |  | 0 | [8 empty] | -600 |  | -600
BT1 |  |  | -1200 |  |  | -4500 | [5 empty] | -600 |  | -6300
BT2 |  | 2100 | 0 | [5 empty] | 0 |  |  |  |  | 2100
BT3 |  | 2100 |  | -1800 | [7 empty] | -600 |  | -300
CT1 |  |  | 1500 | -1800 |  | 0 | [6 empty] | 0 | -300
CT2 |  |  |  | -1800 |  |  |  |  | -25200 |  |  | -600 |  | -27600
CT3 |  | 2100 | 0 | [8 empty] | -600 |  | 1500
CT4 |  |  |  | -1800 | [7 empty] | -600 |  | -2400
CT5 |  | 2100 | [9 empty] | -600 |  | 1500
DT1 | 0 |  |  | -1800 | 28500 |  | 2700 | [6 empty] | 29400
DT2 | 0 |  |  | -1800 | [5 empty] | 0 |  | -600 |  | -2400
DT3 | 0 | [8 empty] | -4500 |  | -600 |  | -5100
DT4 | 0 |  |  | -1800 | [7 empty] | -600 |  | -2400
ET1 | 0 |  | -3000 | [8 empty] | -600 |  | -3600
ET2 |  |  |  | -1800 |  |  |  | 42240 |  |  | 0 | -600 |  | 39840
Grand Total | 0 | 8400 | -4800 | -14400 | 28500 | -4500 | -8100 | 42240 | -25200 | -4500 | 0 | -7200 | -1050 | 9390

## Personal Cost the most and less
Row Labels | Sum of Cost $ / hr | Cost Impact | Time Impact | Count of Task
Monique | 420 | -25200 | -240 | 4
George | 480 | -14400 | -240 | 8
Jim | 180 | -8100 | -90 | 2
Stanley | 600 | -7200 | -144 | 12
Gail | 400 | -4800 | -96 | 8
Jenny | 225 | -4500 | -60 | 3
Sarah | 150 | -4500 | -60 | 2
Tom | 70 | -1050 | -30 | 2
Crystal | 600 | 0 | 0 | 5
Sondra | 45 | 0 | 0 | 1
Erica | 560 | 8400 | 60 | 4
Inigo | 95 | 28500 | 300 | 1
Larry | 88 | 42240 | 480 | 1
Grand Total | 3913 | 9390 | -120 | 53

## Sheet1
JPMC GFBM Virtual Experience Program
Task 1 - Data Analysis
Hypothetical Project Cost - Budget vs. Actual
[5 empty] | Budget Hours | [6 empty] | Actual Hours | [7 empty] | Budget Cost | [6 empty] | Actual Cost
| Project | Task | Resource | Cost $ / hr | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Budget Hour | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Actual Hour | Time Impact | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Budget Cost | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Total Actual Cost | Cost Impact
| Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 24 | 24 | 24 | 30 | 30 | 30 | 162 | -42 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 8100 | -2100
| Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 90 | 90 | 90 | 510 | -30 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150 | 17850 | -1050
| Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | 0
| Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 0 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 0
| Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 840 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | -120 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 75600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 86400 | -10800
| Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 0
| Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 0 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 0
| Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 0
| Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 24 | 24 | 24 | 24 | 24 | 24 | 144 | -24 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | -1200
| Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | -60 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500 | -4500
| Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 1500 | 250 | 250 | 250 | 250 | 250 | 250 | 1500 | 0
| Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 0 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 25200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 25200 | 0
| Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 15 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500 | 2100
| Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 15 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500 | 2100
| Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 250 | 250 | 250 | 250 | 250 | 250 | 1500 | 1500
| Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 0 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800 | 0
| Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 0
| Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 120 | 120 | 120 | 120 | 120 | 120 | 720 | -240 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 50400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 75600 | -25200
| Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | 0
| Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 15 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500 | 2100
| Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 15 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500 | 2100
| Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 15 | 15 | 15 | 15 | 15 | 15 | 90 | 30 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 10800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 8100 | 2700
| Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 110 | 110 | 110 | 110 | 110 | 110 | 660 | 300 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 91200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450 | 62700 | 28500
| Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 0
| Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 0
| Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 0
| Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 90 | 90 | 90 | 90 | 90 | 90 | 540 | -60 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 40500 | -4500
| Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 0
| Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800
| Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 0
| Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | -60 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 12000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 15000 | -3000
| Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 0
| Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 0 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 43200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 43200 | 0
| Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 480 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 84480 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040 | 42240 | 42240
| Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | -12 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600 | -600
| Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | -30 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | -1800

## Sheet2
Which projects are over or under budgeted hours?
Which projects are over or under budgeted costs?
Which personnel are over or under budgeted hours?
Which personnel cost the most? The least?